## Hoja1
Feature | Description | State | Duration
Products Components | Show list of products on the home page | Done | 2
Filter Component | filter products based on their sizes and sort by price | Done | 2 | time | 35 | Hours
Cart Component | Show selected items in the cart on the right sidebar | Done | 3 | Rate | 30 | USD/Hours
Checkout Form | Show checkout form to get buyer data | Done | 2
Add Animation | Animated prodcuts list and adding to cart | Active | 2 | Cost | 1050 | USD
Add Model | Show modal when user click on a product | Active | 2
Products Back end | create a simple backend to send products to front end | Open | 3
Add Redux | create store, initial state and reducer and redux devtool | Open | 2
Add Redux To Products | Move products state to redux | Open | 3
Add Redux To Filter | Move filter state to redux | Open | 3
Add Redux To Cart | Move cart state to redux | Open | 3
Create Order | Handle frondend end backend of creating an order | Open | 3
Add Admin Section | Use react-router to create two router for Home and Admin | Open | 2
Publish on Heroku | Create Mongodb atlas database and publish Heroku app | Open | 3